## Gantt Chart
Theater Recommendation System - Project Timeline
Project Duration: 10/10/2025 - 27/12/2025 (Fall Semester)
Week | Task | Start | End | Owner | 10/10 | 11/10 | 12/10 | 13/10 | 14/10 | 15/10 | 16/10 | 17/10 | 18/10 | 19/10 | 20/10 | 21/10 | 22/10 | 23/10 | 24/10 | 25/10 | 26/10 | 27/10 | 28/10 | 29/10 | 30/10 | 31/10 | 01/11 | 02/11 | 03/11 | 04/11 | 05/11 | 06/11 | 07/11 | 08/11 | 09/11 | 10/11 | 11/11 | 12/11 | 13/11 | 14/11 | 15/11 | 16/11 | 17/11 | 18/11 | 19/11 | 20/11 | 21/11 | 22/11 | 23/11 | 24/11 | 25/11 | 26/11 | 27/11 | 28/11 | 29/11 | 30/11 | 01/12 | 02/12 | 03/12 | 04/12 | 05/12 | 06/12 | 07/12 | 08/12 | 09/12 | 10/12 | 11/12 | 12/12 | 13/12 | 14/12 | 15/12 | 16/12 | 17/12 | 18/12 | 19/12 | 20/12 | 21/12 | 22/12 | 23/12 | 24/12 | 25/12 | 26/12 | 27/12
WEEK 1 | Project Kickoff & Research | 10/10/2025 | 16/10/2025 | Shared
| Define project scope | 10/10/2025 | 12/10/2025 | Shared
| Research existing systems | 10/10/2025 | 14/10/2025 | Özge
| Development environment setup | 13/10/2025 | 16/10/2025 | Özge
| Prepare project proposal | 14/10/2025 | 16/10/2025 | Shared
| Friday presentation prep | 16/10/2025 | 16/10/2025 | Shared
WEEK 2 | Data Collection & Basic Implementation | 17/10/2025 | 23/10/2025 | Shared
| Web scraping development | 17/10/2025 | 20/10/2025 | Özge
| Google Calendar API integration | 17/10/2025 | 21/10/2025 | Özge
| Database schema creation | 19/10/2025 | 22/10/2025 | Özge
| Zero-shot prompting implementation | 20/10/2025 | 23/10/2025 | Özge
| Friday presentation prep | 23/10/2025 | 23/10/2025 | Shared
WEEK 3 | Core Recommendation Engine | 24/10/2025 | 30/10/2025 | Shared
| Few-shot prompting development | 24/10/2025 | 27/10/2025 | Özge
| Google Maps API integration | 25/10/2025 | 28/10/2025 | Özge
| Scoring algorithm | 27/10/2025 | 29/10/2025 | Özge
| Testing with 10 sample plays | 28/10/2025 | 30/10/2025 | Özge
| Friday presentation prep | 30/10/2025 | 30/10/2025 | Shared
WEEK 4 | Agentic Patterns Implementation | 31/10/2025 | 06/11/2025 | Shared
| Tool calling loop development | 31/10/2025 | 03/11/2025 | Özge
| Planner architecture | 01/11/2025 | 04/11/2025 | Özge
| Reflection loop integration | 03/11/2025 | 05/11/2025 | Özge
| Integrate all components | 04/11/2025 | 06/11/2025 | Shared
| Friday presentation prep | 06/11/2025 | 06/11/2025 | Shared
WEEK 5 | Chain-of-Thought & Content Discovery | 07/11/2025 | 13/11/2025 | Shared
| CoT prompting implementation | 07/11/2025 | 10/11/2025 | Özge
| YouTube API integration | 08/11/2025 | 11/11/2025 | Özge
| UI development (Streamlit) | 09/11/2025 | 12/11/2025 | Özge
| Feedback mechanism | 11/11/2025 | 13/11/2025 | Özge
| Friday presentation prep | 13/11/2025 | 13/11/2025 | Shared
WEEK 6 | Evaluation & Testing | 14/11/2025 | 20/11/2025 | Shared
| User testing (5 participants) | 14/11/2025 | 18/11/2025 | Shared
| Metrics collection and analysis | 15/11/2025 | 19/11/2025 | Ayşegül
| Prompting techniques comparison | 16/11/2025 | 19/11/2025 | Özge
| Performance benchmarking | 17/11/2025 | 20/11/2025 | Ayşegül
| Friday presentation prep | 20/11/2025 | 20/11/2025 | Shared
WEEK 7 | Final Integration & Documentation | 21/11/2025 | 27/12/2025 | Shared
| Travel module integration | 21/11/2025 | 28/11/2025 | Ayşegül
| Documentation writing | 24/11/2025 | 10/12/2025 | Shared
| Final presentation preparation | 05/12/2025 | 20/12/2025 | Shared
| Deploy to Streamlit Cloud | 10/12/2025 | 15/12/2025 | Özge
| Final report writing | 15/12/2025 | 26/12/2025 | Shared
| FINAL PRESENTATION & SUBMISSION | 27/12/2025 | 27/12/2025 | Shared
Task Assignment:
Özge | Ayşegül | Shared

## Risk Management
6. Budget & Cost Risks
Risk | Impact | Probability | Mitigation Strategy
API Costs Exceed Budget | Medium | Low | • Free tier limits tracked<br>• Use cheaper alternatives (OSRM, Haiku)<br>• Monthly spending alerts
Unexpected API Charges | Low | Low | • Set billing alerts ($10 threshold)<br>• Use Google Cloud free credits ($200)
5. Project Timeline Risks
Risk | Impact | Probability | Mitigation Strategy
Week 3-4 Delays (API integration complex) | High | Medium | • Prototype with mock data first<br>• Prioritize core features<br>• Skip optional features if needed
Final Week Crunch (Integration issues) | Medium | Medium | • Weekly testing milestones<br>• Buffer time in schedule<br>• Modular architecture
4. User Experience Risks
Risk | Impact | Probability | Mitigation Strategy
Poor Recommendation Quality (New users with no history) | Medium | High | • Zero-shot mode for new users<br>• Ask onboarding preferences<br>• Popular plays as defaults
Privacy Concerns (Calendar access) | High | Medium | • OAuth2 read-only access<br>• Clear privacy policy<br>• Easy revocation process
Slow Response Time (>10 sec) | Medium | Medium | • Optimize prompts<br>• Parallel API calls<br>• Loading indicators
3. Integration Risks
Risk | Impact | Probability | Mitigation Strategy
Calendar API Downtime | Medium | Low | • Graceful degradation (continue without calendar)<br>• Manual date input option
Maps API Changes/Costs | Medium | Medium | • Use OSRM as free alternative<br>• Haversine formula fallback
YouTube API Quota Exceeded | Low | Low | • Optional feature (not critical)<br>• Cache interview links
2. Data Quality Risks
Risk | Impact | Probability | Mitigation Strategy
Outdated Play Information | High | High | • Daily web scraping schedule<br>• Userreported corrections<br>• Cross-verify multiple sources
Incomplete Theater Database | Medium | Medium | • Prioritize major venues first<br>• Expand gradually (50+ plays target)<br>• Usersubmitted plays feature
Web Scraping Failures (Site structure changes) | Medium | Medium | • Modular scraper design <br>• Error notifications<br>• Manual backup process
1.Technical Risks
Risk | Impact | Probability | Mitigation Strategy
API Rate Limits (Google Calendar, Maps) | High | Medium | • Use caching (Redis)<br>• Batch requests<br>• Fallback to OSRM (free)
LLM Hallucinations (Incorrect recommendations) | Medium | Medium | • Few-shot prompting with examples<br>• Reflection loop for self-correction<br>• User feedback validation
Model Cost Overrun (Claude API expensive) | Medium | Low | • Use Haiku (cheaper model)<br>• Cache repeated queries<br>• Set monthly budget limit